## Slide 1: Project of a Mobile Communications’ Base Station in a City near the Spanish Border
João S. Melo - 73223
Manuel L. Ribeiro - 73773
Miguel P. Rodrigues - 73570
Rúben G. Borralho - 73536
Rúben M. Tadeia - 75268
16th May 2016
Notes: Tirar a numeração de paginas na capa

## Slide 2: Outline
Introduction.
Objectives.
Stakeholders.
Scope and Work Breakdown Structure (WBS).
Scheduling.
Resources allocation.
Communication Plan.
Risk Analysis.
Project Closing.
Conclusion.

## Slide 3: Introduction
Plan a Base Station Implementation from the Project Manager´s point of view.
Project Management Methodologies.

## Slide 4: Objectives (1)
Project Objective – Scope:
The planning, implementation and post
monitoring of the Base Station near the
Spanish border.

## Slide 5
Objectives (2)
Project Charter:
  Formal document authorizing the project;
  Stakeholders necessities and expectations;
  Business case: Technological Advance;
  Project as a part of the Operator’s Strategical Plan.
3G
4G

## Slide 6
Internal:
  Project Leader;
  Management Department;
  Radio Eng. Department;
  Regulation Department;
  Law Department;
  Marketing Department;
  Buying Department.
Stakeholders (1)

## Slide 7
External:
  Contracted Entities:
    Constructor;
    Electric Energy Supplier;
    Owner;
    Negotiator;
    Fixed Link Supplier;
    Equipment Supplier.
  Non-Contracted Entities:
    ANACOM;
    Municipality;
    Spanish Operators.
Stakeholders (2)

## Slide 8
Scope Requirements:
  Covered range;
  Bandwidth;
  Bitrate;
  Generation upgrade;
  ANACOM and ITU-T norms and recommendations;
  Legal requirements;
  Keep network unchanged;
  Conformance with Spanish operator´s frequencies.
Scope and WBS (1)

## Slide 9
Scope and WBS (2)
Initial Project
Planning
Location Study
Construction Project
and Legalities
Project of a Mobile Communications’ Base Station in a City near the Spanish Border - WBS

## Slide 10
Scope and WBS (3)
Telecommunications
Engineering Project
Integration and
Test
Construction
Project Closing

## Slide 11
Scheduling (1)
Important Dates
03/03/2016
22/06/2016
20/04/2016
14/03/2016
Important Diagrams
  Gantt
  PERT
List of Task and resources

## Slide 12
Our team
Scheduling (2)
Good Communication
Brainstorming
Contributed to
Lead to
[Fonte: Socialbox, 2015]

## Slide 13
Scheduling (3)
What was our focus?
Setting Goals
Stakeholders
Site visit
Negotiations
Planning
Study
8 Days
7 Days

## Slide 14
Scheduling (4)
What was our focus?
23 Days
10 Days
Construction
End
Base Station Construction
Building Process
Remote Monitoring
Project Closing

## Slide 15
Internal Stakeholders
Resources Allocation (1)
External Stakeholders
  Total estimated costs: € 43 388,40
Stakeholder
Leader
Radio D.
Management D.
Law D.
Regulation D.
Buying D.
Marketing D.
Workers
Cost
100€/h
75€/h
75€/h
50€/h
50€/h
50€/h
75€/h

## Slide 16
Resources Allocation (2)
Cash Flow Table (in thousands)
Total Cost: € 202 106,92

## Slide 17
Communication Plan
External Communication Plan
  Formal communications;
  Scheduled when necessary and in agreement with previous WBS definition.
  Crucial communications:
    Reports;
    Official meetings.
Internal Communication Plan
  Daily communications:
    Personal Calls;
    Email.

## Slide 18
Avoid.
Mitigate.
Transfer.
Accept.
Risk Analysis
Future Uncertainty
Risk examples:
Answer/ Construction/ Licensing Delays;
Price Variations;
Engineering Errors.

## Slide 19
Continuous Monitoring.
Periodic Visits.
Contract Closing.
Performance evaluation:
  Total Cost: € 202 106,92.
  Duration: 80 days.
Knowledge Management.
Project Closing

## Slide 20
Project managers inside view.
Project Management (PM) Typical Procedures.
Critical Analysis on the various PM strategies.
Conclusion